## Group 9
Group Plan
Week | Meeting Date | Topics | Presenting
2 | 2018-09-28 | Get organized, make a plan, make decissions.
3 | 2018-10-02 | 1. JavaScript – Loops, Conditional Statements, Functions, Arrays 2. JavaScript – Object Creation Functions, Properties, Methods, Instantiation | Addison Steinagel Perry Raleigh
4 | 2018-10-09 | 3. JSON Parse, Stringify 4. Using AJAX to Consume a JSON Web Service | Daniel Tujillo Thomas Vargas
5 | 2018-10-16 | 5. Local Storage Storing and Retrieving Arrays, Associative Arrays, and Objects | Addison Steinagle
6 | 2018-10-23 | 6. DOM Manipulation Using createElement, appendChild, insertBefore etc. | Perry Raleigh
7 | 2018-10-30 | 7. Manipulating CSS Class Properties Using JavaScript 8. CSS3 Transitions and Animations and triggering them with JavaScript | Daniel Tujillo Thomas Vargas
8 | 2018-11-06 | 9. JavaScript Events Especially for Mobile Devices (onTouchBegin) and Animation and Transition Events | Addison Steinagle
9 | 2018-11-13 | 10. HTML5 Tags - Video, Audio, and Canvas 11. Designing, Defining, and Triggering CSS3 Transitions without Custom Libraries | Perry Raleigh Daniel Tujillo
10 | 2018-11-20 | 12. Designing, Defining, and Triggering CSS3 Transforms without Custom Libraries 13. Designing, Defining, and Triggering CSS3 Animations without Custom Libraries | Thomas Vargas Addison Steinagle
11 | 2018-11-27 | App design descision must be completed. Work together to add techonolgies from topics #1 - #5 into the app by next meeting. | Perry Raleigh
12 | 2018-12-04 | Work together to add techonolgies from topics #6 - #10 into the app by next meeting. | Daniel Tujillo
13 | 2018-12-11 | Work together to add techonolgies from topics #11 - #13 into the app by next meeting. | Thomas Vargas
14 | 2018-12-18 | Review, summarize what was learned, submit our journals. May not need to meet for this one.
Formulas:
Meeting Date = [Meeting Date, row above]+7
We will use Slack for our primary method of communicating and collaborating asynchronously.
We have a Github repository setup for the group to allow us to share documents and code snippets with the group.
The Agile methodology we selected is Scrum. Each week will be a sprint and we will adapt our daily Scrum to be asynchronous by using Slack.
Since we missed presenting this week, we will have to double down on most of the coming weeks.

## My Plan
Personal Schedule
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Week 1 (Sep 17-23)
Week 2 (Sep 24-30)
Personal Study
Week 3 (Oct 1-7) | [7 empty] | Meet with my group
Interact with my instructor
Week 4 (Oct 8-14)
Provide documentation to my instructor
Week 5 (Oct 15-21)
Week 6 (Oct 22-28)
Week 7 (Oct 29-Nov 4)
Week 8 (Nov 5-11)
Week 9 (Nov 12-18)
Week 10 (Nov 19-25)